## Account Statement
FINANCIAL STATEMENT OF BILL OF QUANTITIES DIRECT LABOUR FOR 500KW MINING SETUP FACILITY IN BAYELSA
S/N | Description | QTY | Unit | Price | Amount | Omission | Addition | Next Procure | Subcontractor
Site Preparation and Civil works
A | Clearing of site by removing all shrubs |  | Sum |  | 0 | 0
and bushes
B | Bulk excavation for Concrete Poles (4) |  | Sum |  | 170000 | 170000
with hanging and Earthing
C | Pad Foundation Excavation |  | Sum |  | 150000 | 150000
D | Concrete base for transformer |  | Sum |  | 244000 | 244000
E | Concrete in Pad Foundation for Container |  | Sum |  | 450000 | 450000
F | Y12 Reinforcement bar in Pad Foundation |  | Sum |  | 210000 | 210000
| Site Preparation carried to Summary |  |  |  | 1224000 | 1224000 |  | 0
TRANSFORMER ACCESSORIES AND INSTALLATION
A | concrete Poles | 4 | Nr | 170000 | 680000 | 0 |  |  | 680000
B | Installation of Poles | 4 | Nr | 60000 | 240000 | 0 |  |  | 240000
C | Gang isolator | 1 | Nr | 450000 | 450000 | 450000
D | 50mm iron pipe for gang Isolator Contorl | 1 | Nr | 45000 | 45000 | 45000
E | Aluminium conductor | 150 | m | 3800 | 570000 | 570000
F | 800Ampere Feeder Pillar | 1 | Nr | 750000 | 750000 | 750000
G | Disk insulator | 8 | Nr | 14000 | 112000 | 112000
H | U-Channel | 8 | Nr | 55000 | 440000 | 440000
I | angle Channel | 6 | Nr | 42000 | 252000 | 252000
J | Barrel Insulator | 6 | Nr | 3700 | 22200 | 22200
K | 10 inch Bolt and Nut | 10 | Nr | 8000 | 80000 | 80000
L | 9 inch Bolt and Nut | 30 | Nr | 7500 | 225000 | 225000
M | Stay wire | 3 | Nr | 7000 | 21000 |  | 48000
N | 70mm single core Pvc Cable | 16 | m | 13500 | 216000 | 216000
O | 70mm single core naked copper for Earthing | 150 | m | 7500 | 1125000 | 0
P | Lighting Arestor | 1 | Nr | 130000 | 130000 | 130000
Q | 500mm Single Core Armored cable | 40 | m | 87000 | 3480000 | 0
T | Cable Lock
i | 500mm Cable lugs | 16 | Nr | 16000 | 256000 | 0
ii | 70mm Cable lugs | 6 | Nr | 3200 | 19200 | 19200
iii | Cable Lock Machine | 1 | Nr | 70000 | 70000 | 70000
Q | 70mm single core naked copper for Earthing | 150 | m | 13500 | 2025000 |  | 2025000
S | 400mm Single Core Armored cable | 40 | m | 85000 | 3400000 |  | 3400000
T | Cable Lock
i | 400mm Cable lugs | 16 | Nr | 16000 | 256000 |  | 256000
[5 empty] | 9183400 | 3381400 | 5729000
3381400
9110400
A | 2m long pointed Earth Rod | 10 | Nr | 10000 | 100000 | 100000 | 20000
B | Installation of Transformer and Builders work |  | Sum |  | 1700000 | 0 |  | 1700000
C | certification of NEMSA |  | Sum |  | 1200000 | 0 |  | 1200000
D | Testing of the Transformer |  | Sum |  | 590000 | 0 |  | 590000
E | Transportation of cables |  | Sum |  | 650000 | 0
F | Fencing of Transformer including barb wire and |  | Sum |  | 457000 | 0 |  | 457000
Danger Sign with Granite as floor Finishing
F | Copper Feeder Unit | 2 | Nr | 100000 | 200000 |  | 200000
B | 11KV Difuse | 1 | Nr | 150000 | 150000 |  | 150000
G | 400 Amp Fuse | 10 | Nr | 12000 | 120000 |  | 120000
H | Fuse Removal | 1 | Nr | 3000 | 3000 |  | 3000
[5 empty] | 4697000 | 100000 | 493000
100000
593000
| Page 3 |  |  |  | 9183400 |  | 9110400
| Page4 |  |  |  | 4697000
500KW 11 TRANSFORMER ACCESORIES AND
| INSTALLATION Carried to Summary |  |  |  | 13880400 |  | 9703400 | 3947000
20Ft X 8Ft Steel Container Fabrication
for housing Miner (3Nrs)
METAL
B | 2'' X 2'' Steel pipe | 30 | Nr | 17500 | 525000 | 525000
C | 1 1/2 Steel Pipe | 12 | Nr | 7800 | 93600 | 93600
D | 3/4 Steel pipe | 40 | Nr | 3900 | 156000 | 156000
E | 06.8 Steel Black sheet | 38 | Nr | 28000 | 1064000 | 1064000
G | 1'' X 1'' Steel pipe | 28 | Nr | 4200 | 117600 | 117600
H | Net wire | 5 | Nr | 17000 | 85000 | 85000
J | Flat bar | 2 | Nr | 7500 | 15000 | 15000
| Electrode | 6 | Nr | 9000 | 54000 | 54000
K | Gloss Paint | 20 | Litres | 3400 | 68000 | 68000
L | Transportation of Steel Materials |  | Sum |  | 720000 | 720000
M | Builders work for Steel Container Fabrication |  | Sum |  | 520000 | 520000
and Erection
N | Wood Work For Floor Insulator
i | Marine board for Container floor | 7 | Nr | 25000 | 175000 | 175000
ii | 50X100 Hard wood | 19 | Nr | 800 | 15200 | 15200
iii | Iron Net | 4 | Bundle | 17000 | 68000 | 68000
iv | 50X25mm Hard wood | 15 | Nr | 700 | 10500 | 10500
v | Pattern wood | 20 | Nr | 350 | 7000 | 7000
vi | Nail | 28 | Kg | 450 | 12600 | 12600
vii | Builder work for container floor Finishing |  | Sum |  | 110000 | 0 |  | 110000
20Ft X 8ft Steel Container and wooden floor Finish
| Carried to Summary |  |  |  | 3816500 | 3706500 |  | 110000
Wiring of Container, Ethernet Connection
and Security hardwares
A | 800 Ampere Breaker, 160A breaker and Copper bar | 1 | Nr | 957000 | 957000 | 957000
B | 16mm single core copper wire | 4 | Bundle | 375000 | 1500000 | 1500000
C | 16mm cable lock | 2 | Bundle | 15000 | 30000 | 30000
D | 2inch X 3inch PVC Trunking | 4 | Nr | 6500 | 26000 | 26000
E | 1 1/2inch X 2inch PVC Trunking | 2 | Nr | 3200 | 6400 | 6400
F | WLan Cable | 1 | Bundle | 45000 | 45000 | 0 |  | 45000
G | WLan Connector (RG47) | 2 | Bundle | 25000 | 50000 | 0 |  | 50000
H | WLan Remote Tester | 2 | Nr | 24000 | 48000 | 0 |  | 48000
J | Network cable cripping tool (slicing tools) | 2 | Nr | 3000 | 6000 | 0 |  | 6000
K | 48 Ports Ethernet switch | 3 | Nr | 138000 | 414000 | 0 |  | 414000
L | Power Distribution Unit 12pots | 12 | Nr | 450000 | 5400000 | 0 |  | 5400000
N | 100w halogen security light | 6 | Nr | 40000 | 240000 | 240000
O | Builders work for Wiring and Ethernet |  | Sum |  | 320000 | 0 |  | 320000
Connection
B | 10mm single core copper wire (Black) | 1 | Bundle | 200000 | 200000 |  | 200000
D | 1.5mm 3core wire | 3 | Bundle | 22000 | 66000 |  | 66000
E | 1mm 2core wire | 2 | Bundle | 9000 | 18000 |  | 18000
F | Electrical tape 4 Colours | 4 | Bundles
G | Scotch Tape | 3 | Nrs | 3500 | 10500 |  | 10500
H | Surge Extension Box | 2 | Nr | 9000 | 18000 |  | 18000
J | 13A Socket and Panteres | 3 | Nr | 3500 | 10500 |  | 10500
K | Lamp holder | 6 | Nr | 500 | 3000 |  | 3000
L | Light switch | 4 | Nr | 1500 | 6000 |  | 6000
M | 20W bulb | 6 | Nr | 4500 | 27000 |  | 27000
| 35mm Cable lug | 1 | Bundle | 23000 | 23000 |  | 23000
| 10Amps primary fuse | 2 | Set | 10000 | 20000 |  | 20000
| Earth mat | 2 | Nr | 170000 | 340000 |  | 340000
| Tool Box | 1 | Nr | 160000 | 160000 |  | 160000
| Hand Drill Machine | 1 | Nr | 48000 | 48000 |  | 48000
| 300 Cable log | 1 | Nr | 45000 | 45000 |  | 45000
| Safety Boot | 4 | Nr | 14500 | 58000 |  | 58000
| Overall | 4 | Nr | 11000 | 44000 |  | 44000
| Clamp meter | 1 | Nr | 10000 | 10000 |  | 10000
| Drill Bit | 1 | Set | 15000 | 15000 |  | 15000
| Hand Glove | 1 | Dozen | 8000 | 8000 |  | 8000
| 12mm Allen Key | 1 | Nr | 4000 | 4000 |  | 4000
| 14mm Allen Key | 1 | Nr | 4000 | 4000 |  | 4000
| 15mm Allen Key | 1 | Nr | 4500 | 4500 |  | 4500
| M19 | 6 | Nr | 195 | 1170 |  | 1170
| M17 | 12 | Nr | 160 | 1920 |  | 1920
| M17 Inch | 12 | Nr | 150 | 1800 |  | 1800
| M10 | 20 | Nr | 135 | 2700 |  | 2700
[6 empty] | 2759400 | 1150090
2759400
3909490
Wiring of Container, Ethernet Connection and Security
| Carried to Summary |  |  |  | 10192490 |  | 3909490 | 6283000
PREMISES FENCING WITH STEEL POLES AND BOARD
A | Steel Pole | 30 | Nr | 21000 | 630000 | 630000
B | Wire Net | 10 | Bundle | 40000 | 400000 | 400000
C | Aluco Partition Board | 80 | Nr | 22500 | 1800000 | 1800000
D | Cement | 20 | Nr | 8500 | 170000 | 170000
E | Sand | 5 | Ton | 32000 | 160000 | 160000
F | Granite | 15 | Ton | 45000 | 675000 | 675000
G | Barb wire net | 6 | Bundle | 17000 | 102000 | 102000
H | Steel gate | 1 | Nr | 370000 | 370000 | 370000
J | Binding Wire | 2 | Bundle | 25000 | 50000 | 50000
A | Steel Pole | 10 | Nr | 21000 | 210000 |  | 210000
| Builders work |  | Sum |  | 450000 | 450000
[6 empty] | 4807000 | 210000
4807000
| PREMISES FENCING CARRY TO SUMMARY |  |  |  | 5017000 |  | 5017000 | 0
SECURITY HOUSE
A | 2'' X 2'' Steel pipe | 10 | Nr | 17500 | 175000 | 175000
B | 1 1/2 Steel Pipe | 22 | Nr | 7800 | 171600 | 171600
C | 06.8 Steel Black sheet | 15 | Nr | 28000 | 420000 | 420000
D | Gloss Paint | 5 | Litres | 3400 | 17000 | 17000
| Flash Bar | 2 | Carton | 7500 | 15000 |  | 7500
| 3/4 Round pipe | 6 | Nr | 21000 | 126000 |  | 126000
| Angle five | 3 | Nr | 19000 | 57000 |  | 57000
| Builders work |  | Sum |  | 1200000 | 0 |  | 1200000
| Builders work |  | Sum |  | 350000 | 0 | 350000 | 350000
[6 empty] | 783600 | 540500
783600
| SECURITY HOUSE TO SUMMARY |  |  |  | 2531600 |  | 1324100 | 850000
Summary
2 | Site Preparation and Civil works |  |  |  | 1224000 |  | 1224000 | 0
3 | 500KW 11 TRANSFORMER ACCESSORIES AND INSTALLATION |  |  |  | 13880400 |  | 9703400 | 3947000
4 | Steel Container and wooden floor Finish |  |  |  | 3816500 |  | 3706500 | 110000
5 | Wiring of Container and Ethernet Connection |  |  |  | 10192490 |  | 3909490 | 6283000
6 | Premises Fencing |  |  |  | 5017000 |  | 5017000 | 0
7 | Security House |  |  |  | 2531600 |  | 1324100 | 850000
| TOTAL SUM IN NAIRA |  |  |  | 36661990 |  | 24884490 | 11190000
| TOTAL SUM IN USD |  |  |  | 25284.131 |  | 17161.7172 | 7460
| ADD 10% PROFESSIONAL FEE |  |  |  | 2528.4131 |  | 1716.1717
| TOTAL |  |  |  | 27812.5441

## Traveling and Accomodation
S/N | Description | Day/Numbers | Cost | Amount (N)
1 | Flight Cost | 4 | 150000 | 600000
2 | Hotel at Porthacourt | 4 | 25000 | 100000
3 | Transport from Portacourt to Bayelsa | 2 | 30000 | 60000
4 | Hotel at Yenogua | 2 | 25000 | 50000
5 | Food at Porthacourt | 4 | 14000 | 56000
6 | Speed Bolt Transport to Ogbinbiri | 2 | 95000 | 190000
7 | Hotel at ogbinbiri | 8 | 10000 | 80000
8 | Food at Ogbinbiri | 8 | 12500 | 100000
| Subtotal |  |  | 1236000
| Total in USD |  |  | 852.4138

## GENERAL SUMMARY
S/N | DESCRIPTION | QTY | Unit | Price | Amount (USD)
GENERAL SUMMARY
1 | Project |  |  |  | 17161.7172
2 | Traveling and Accomodation |  |  |  | 852.4138
| TOTAL COST INCURRED |  |  |  | 18014.131
| PAYMENT |  |  |  | 18800
| Balance Left |  |  |  | -785.869
| Professional Fee |  |  |  | 1716.1717
| Balance Left to be Paid |  |  |  | 930.3028

## PAYMENT AND DATE
Payment Made
S/N | DESCRIPTION | QTY | Unit | Price | Amount (USD)
1 | 16th August 2024 |  |  |  | 5000
2 | 16th August 2024 |  |  |  | 11000
3 | 23rd August 2024 |  |  |  | 2800
| Total Sum |  |  |  | 18800